## ProjectTeam
Name | GitHub Alias
Pascal Zaugg | pas
Lukas von Rotz | lukasvonrotz
Andreas Hohler | papagei9
Karan Sethi | karans13
Adrian Kurt | Lafunamor

## ProductBacklog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | Questions
1 | Login | User can log into existing account | high | 2 |  |  | open
2 | Register | User can register on the platform (height, weight, location, preferences, etc.) | high | 1 |  |  | open
3 | subscribe to sport | User can subscribe to one or more sports (soccer, cycling, boxing, soccer) | low | 3 |  |  | open
4 | create trainings | User can create, edit and delete a training with location, time, outside/inside and training level properties of a sport he's subscribed to. | high | 4 |  |  | open | What are the properties of a training?
5 | log training | user can log infomation about the training like length, well-beeing, fitness level. | high | 5 |  |  | open | Could we utilize an already existing app to do the tracking and then use the data of that application? Endomondo, Runtastic, Nike+ Running
6 | view statistics | user can see statitics about his trainings like number of trainings, average training time | high | 8 |  |  | open | What properties are listed in the statistic?
7 | public training | User can create, edit and delete public trainings | high | 2 |  |  | open
8 | find trainings | User can find public listed trainings | high | 2 |  |  | open
9 | find partners | User can join public trainings (a new team is formed) | high | 2 |  |  | open
10 | schedule training with partner | teams can have trainings | high | 3 |  |  | open | Are teams something like organisations in github? Or do they only exist as long the training exists?
11 | log training with partner | information for team-trainings can be logged | medium | 3 |  |  | open
12 | user can create teams | user can invite other users to trainings | medium | 1 |  |  | open
13 | teams can schedule trainings | teams can have a team-training | medium | 2 |  |  | open
14 | training location | the user can specify the training location | high | 1 |  |  | open
15 | location weather | Trainings with locations show weather information. Subscribed members get a message if the weather cast is bad one day before the outside training. | medium | 3 |  |  | open
16 | location map | trainings with location show a map of the trainingplace | medium | 2 |  |  | open
17 | Calendar | User can see a calendar with scheduled trainings and can subscribe to it (.ical Feed) | medium | 2 |  |  | open
18 | Compare Trainings | User can compare his training with others. | medium | 3 |  |  | open
19 | Training suggestions | User gets suggestions for a public training depending on his location and his past trainings. | low | 6 |  |  | open
20 | Email Notifcations | User can create Email Notifications and gets an email a specified time before the training starts. | medium | 6 |  |  | open
21 | Weekly Trainings | User can create repeating weekly trainings. | medium | 12 |  |  | open
22 | Training rating | User can comment on trainings and rate them. | medium | 1 |  |  | open
23 | Message Service | User can send a message to another user. | medium | 10 |  |  | open
24 | Team trainings settings | User can set a maximum and a minimum of members needed for a training. No more than the set maximum can join a training. If the minimum is not reached before a specified time all joined members get a message that the training is canceled. | medium | 3 |  |  | open
25 | Facebook Login | User can login/register with facebook | high | 8 |  |  | open
26 | Facebook Event creation | User can share the treining as a event on facebook | high | 6 |  |  | open
27 | Traveling time | User sees traveling time to training | medium | 10 |  |  | open
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47

## SprintBacklog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Define Application Structure | Discuss Models, Controllers and Relations | All | All | All | high | 2 |  | 2 | done
1.2 | 1 | Apply Application Structure | Create models & controllers | All | Andreas | All | high | 2 |  | 2 | done
1.2 | 1 | CyberCoach Integration | Analyse CyberCoach Project and Integrate it | All |  | All | high | 6 |  | 0 | waiting
1.3 | 1 | Login & Register & Edit | Devise | Model, Controller | Adrian | All | high | 3 |  | 1 | done
1.4 | 1 | Facebook Integration (Login) | Connection to fb | Model, Controller |  | All | high | 8 |  | 0 | waiting
1.6 | 1 | Initial GUI with Bootstrap | Tune all views with Bootstrap to take as a basis and set template | UI |  | All | high | 3 |  | 1 | work in progress
|  | Training Controller, Training session | Simple functionality | All | Andreas | All | medium | 3 |  | 3 | done

## BurndownChart
Sprint | Time of Record | Ideal Curve | Remaining Effort | Remaining Ressources
1 | 2015-10-06 | 29 | 27 | 31.2
1 | 2015-10-07 | 27.0667 | 25 | 27.2
1 | 2015-10-08 | 25.1333 | 25 | 27.2
1 | 2015-10-09 | 23.2 | 25 | 27.2
1 | 2015-10-10 | 21.2667 | 25 | 27.2
1 | 2015-10-11 | 19.3333 | 21 | 25.2
1 | 2015-10-12 | 17.4 | 19 | 23.2
1 | 2015-10-13 | 15.4667 | 16 | 20.2
1 | 2015-10-14 | 13.5333
1 | 2015-10-15 | 11.6
1 | 2015-10-16 | 9.6667
1 | 2015-10-17 | 7.7333
1 | 2015-10-18 | 5.8
1 | 2015-10-19 | 3.8667
1 | 2015-10-20 | 1.9333
1 | 21.10,2015 | 0