## ProjectTeam
Name | GitHub Alias
Pascal Zaugg | pas
Lukas von Rotz | lukasvonrotz
Andreas Hohler | papagei9
Karan Sethi | karans13
Adrian Kurt | Lafunamor

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | Questions
1 | Login | User can log into existing account |  | 2 |  |  | open
2 | Register | User can register on the platform (height, weight, location, preferences, etc.) |  | 1 |  |  | open
3 | subscribe to sport | User can subscribe to one or more sports (soccer, cycling, boxing, soccer) |  | 3 |  |  | open
4 | create trainings | User can create, edit and delete a training with location, time, outside/inside and training level properties of a sport he's subscribed to. |  | 4 |  |  | open | What are the properties of a training?
5 | log training | user can log infomation about the training like length, well-beeing, fitness level. |  | 5 |  |  | open | Could we utilize an already existing app to do the tracking and then use the data of that application? Endomondo, Runtastic, Nike+ Running
6 | view statistics | user can see statitics about his trainings like number of trainings, average training time |  | 8 |  |  | open | What properties are listed in the statistic?
7 | publish training | User can create, edit and delete public trainings |  | 2 |  |  | open
8 | find trainings | User can find public listed trainings |  | 2 |  |  | open
9 | find partners | User can join public trainings (a new team is formed) |  | 2 |  |  | open
10 | schedule training with partner | teams can have trainings |  | 3 |  |  | open | Are teams something like organisations in github? Or do they only exist as long the training exists?
11 | log training with partner | information for team-trainings can be logged |  | 3 |  |  | open
12 | user can create teams | user can invite other users to trainings |  | 1 |  |  | open
13 | teams can schedule trainings | teams can have a team-training |  | 2 |  |  | open
14 | training location | the user can specify the training location |  | 1 |  |  | open
15 | location weather | Trainings with locations show weather information. Subscribed members get a message if the weather cast is bad one day before the outside training. |  | 3 |  |  | open
16 | location map | trainings with location show a map of the trainingplace |  | 2 |  |  | open
17 | Calendar | User can see a calendar with scheduled trainings and can subscribe to it (.ical Feed) |  | 2 |  |  | open
18 | Compare Trainings | User can compare his training with others. |  | 3 |  |  | open
19 | Training suggestions | User gets suggestions for a public training depending on his location and his past trainings. |  | 6 |  |  | open
20 | Email Notifcations | User can create Email Notifications and gets an email a specified time before the training starts. |  | 6 |  |  | open
21 | Weekly Trainings | User can create repeating weekly trainings. |  | 12 |  |  | open
22 | Training rating | User can comment on trainings and rate them. |  | 1 |  |  | open
23 | Message Service | User can send a message to another user. |  | 10 |  |  | open
24 | Team trainings settings | User can set a maximum and a minimum of members needed for a training. No more than the set maximum can join a training. If the minimum is not reached before a specified time all joined members get a message that the training is canceled. |  | 3 |  |  | open
25 | Facebook Login | User can login/register with facebook |  | 8 |  |  | open
26 | Facebook Event creation | User can share the treining as a event on facebook |  | 6 |  |  | open
27 | Traveling time | User sees traveling time to training |  | 10 |  |  | open
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 2 | Patient Model | Data model for patient record needs to be created based on standard.... | Database | Martin | Hans | medium | 2 | 2 | 0 | waiting
1.2 | 2 |  |  | UI, Controller | Hans | Jennifer | high | 8 | 6 | 4 | work in progress
1.3 | 1 |  |  | All | Martin | Tom | high | 16 | 20 | 20 | done
2.1 | 1 |  |  | Database | Tom | Martin | low | 4 | 10 | 4 | cancelled
2.2 | 2 |  |  | Main Window | Jennifer | Martin | high | 8 | 6 | 5 | work in progress

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180