## ProjectTeam
Name | GitHub Alias
Pascal Zaugg | pas
Lukas von Rotz | lukasvonrotz
Andreas Hohler | papagei9
Karan Sethi | karans13
Adrian Kurt | Lafunamor

## ProductBacklog
ID | Story Name | Description | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | Questions
1 | Login | User can log into existing account | high | 2 |  |  | closed
2 | Register | User can register on the platform (height, weight, location, preferences, etc.) | high | 1 |  |  | closed
3 | subscribe to sport | User can subscribe to one or more sports (soccer, cycling, boxing, soccer) | low | 3 |  |  | closed
4 | create trainings | User can create, edit and delete a training with location, time, outside/inside and training level properties of a sport he's subscribed to. | high | 4 |  |  | closed | What are the properties of a training?
5 | log training | user can log infomation about the training like length, well-beeing, fitness level. | high | 5 |  |  | closed | Could we utilize an already existing app to do the tracking and then use the data of that application? Endomondo, Runtastic, Nike+ Running
6 | view statistics | user can see statitics about his trainings like number of trainings, average training time | high | 8 |  |  | open | sprint 4
7 | public training | User can create, edit and delete public trainings | high | 2 |  |  | closed
8 | find trainings | User can find public listed trainings | high | 2 |  |  | open | sprint 4
9 | find partners | User can join public trainings (a new team is formed) | high | 2 |  |  | closed
10 | schedule training with partner | teams can have trainings | high | 3 |  |  | closed | Are teams something like organisations in github? Or do they only exist as long the training exists?
11 | log training with partner | information for team-trainings can be logged | medium | 3 |  |  | closed
12 | user can create teams | user can invite other users to trainings | medium | 1 |  |  | closed
13 | teams can schedule trainings | teams can have a team-training | medium | 2 |  |  | closed
14 | training location | the user can specify the training location | high | 1 |  |  | closed
15 | location weather | Trainings with locations show weather information. Subscribed members get a message if the weather cast is bad one day before the outside training. | medium | 3 |  |  | work in progress
16 | location map | trainings with location show a map of the trainingplace | high | 2 |  |  | work in progress
17 | Calendar | User can see a calendar with scheduled trainings and can subscribe to it (.ical Feed) | medium | 2 |  |  | open | sprint 5
18 | Compare Trainings | User can compare his training with others. | medium | 3 |  |  | open | sprint 5
19 | Training suggestions | User gets suggestions for a public training depending on his location and his past trainings. | low | 6 |  |  | open | sprint 5
20 | Email Notifcations | User can create Email Notifications and gets an email a specified time before the training starts. | high | 6 |  |  | work in progress
21 | Weekly Trainings | User can create repeating weekly trainings. | medium | 12 |  |  | work in progress
22 | Training rating | User can comment on trainings and rate them. | medium | 1 |  |  | closed
23 | Message Service | User can send a message to another user. | medium | 10 |  |  | open | sprint 4
24 | Team trainings settings | User can set a maximum and a minimum of members needed for a training. No more than the set maximum can join a training. If the minimum is not reached before a specified time all joined members get a message that the training is canceled. | medium | 3 |  |  | open | sprint 4
25 | Facebook Login | User can login/register with facebook | high | 8 |  |  | closed
26 | Facebook Event creation | User can share the treining as a event on facebook | low | 6 |  |  | open | sprint 4
27 | Traveling time | User sees traveling time to training | medium | 10 |  |  | work in progress
28 | GUI | Choose template and integrate it | high | 10 |  |  | open | sprint 5
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47

## SprintBacklog
ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status | Deadline
1.1 | 1 | Define Application Structure | Discuss Models, Controllers and Relations | All | All | All | high | 2 |  | 2 | done
1.2 | 1 | Apply Application Structure | Create models & controllers | All | Andreas |  | high | 2 |  | 2 | done
1.2 | 1 | CyberCoach Integration | Analyse CyberCoach Project and Integrate it | All |  |  | high | 6 |  | 0 | done
1.3 | 1 | Login & Register & Edit | Devise | Model, Controller | Adrian | Karan | high | 3 |  | 1 | done
1.4 | 1 | Facebook Integration (Login) | Connection to fb | Model, Controller | Pascal |  | high | 8 | 12 | 22.2 | done | 3.11.15
1.6 | 1 | Initial GUI with Bootstrap | Tune all views with Bootstrap to take as a basis and set template | UI |  |  | high | 3 |  | 1 | done
1.7 | 1 | Training Controller, Training session | Simple functionality | All | Andreas | Lukas | high | 3 |  | 3 | done
2.1 | 2 | Integrate User Profiles | User can Edit and Display his user profile, userprofiles are public visible | All | Karan |  | high | 2 |  | 5.5 | done | 3.11.15
2.2 | 2 | Login using cybercoach | Login uses CyberCoach service | All | Adrian, Lukas | Lukas, Adrian | ultra | 10 | 12 | 14 | done
2.3 | 2 | Extend training (training session, logs) | Add training sessions and logs functionality inclusive rating | All | Andreas |  | high | 4 |  | 3 | done
2.4 | 2 | Trainings | Subscribe to sport on CyberCoach | Controller | Andreas |  | high | 6 |  | 3 | done | 8.11.15
2.5 | 2 | Training data on CyberCoach | The data of trainings is stored on cybercoach | Controller | Andreas |  | high | 6 |  | 5 | done | 8.11.15
3.1 | 2 | Twitter integration | User can tweet a training | UI, Controller | Pascal |  | low | 6 |  |  | work in progress | 15.11.15
3.2 | 3 | Friendship handling | Users can get friends | All | Lukas |  | medium | 8 |  | 5 | done | 10.11.15
3.3 | 3 | Openweather API | Weather API in seperate Model! | All | Adrian |  | medium | 5 |  |  | work in progress | 15.11.15
3.4 | 3 | GoogleMaps | Google API in seperate Model! | All | Karan |  | medium | 3 |  |  | work in progress | 10.11.15
3.5 | 3 | Transportation | SBB API in seperate Model! | All | Pascal |  | medium | 6 |  |  | work in progress | 15.11.15
3.6 | 3 | Invite to training | Invite a friend to training | All | Lukas |  | medium | 4 |  |  | work in progress | 17.11.15
3.7 | 3 | Weekly trainings |  | All | Andreas |  | medium | 3 |  |  | work in progress | 17.11.15
3.8 | 3 | E-Mail notification | Write Email one day before training starts | All | Karan |  | medium | 3 |  |  | work in progress | 17.11.15

## BurndownChart
Sprint | Time of Record | Ideal Curve | Remaining Effort | Remaining Ressources
1 | 2015-10-06 | 27 | 27 | 31.2
1 | 2015-10-07 | 25.2 | 25 | 27.2
1 | 2015-10-08 | 23.4 | 25 | 27.2
1 | 2015-10-09 | 21.6 | 25 | 27.2
1 | 2015-10-10 | 19.8 | 25 | 27.2
1 | 2015-10-11 | 18 | 21 | 25.2
1 | 2015-10-12 | 16.2 | 21 | 23.2
1 | 2015-10-13 | 14.4 | 21 | 23.2
1 | 2015-10-14 | 12.6 | 21 | 23.2
1 | 2015-10-15 | 10.8 | 19 | 23.2
1 | 2015-10-16 | 9 | 19 | 23.2
1 | 2015-10-17 | 7.2 | 17 | 21.2
1 | 2015-10-18 | 5.4 | 17 | 21.2
1 | 2015-10-19 | 3.6 | 17 | 21.2
1 | 2015-10-20 | 1.8 | 17 | 21.2
1 | 2015-10-21 | 0 | 17 | 0
2 | 2015-10-21 | 42 | 42 | 31.2 | 42: 30h sprint 2 + 12h incomplete FB task from sprint 1
2 | 2015-10-22 | 39 | 42 | 25.2 | AK & LV: discussion login
2 | 2015-10-23 | 36 | 30 | 17.2 | AK & LV: login implementation
2 | 2015-10-24 | 33 | 30 | 17.2
2 | 2015-10-25 | 30 | 30 | 17.2
2 | 2015-10-26 | 27 | 30 | 17.2
2 | 2015-10-27 | 24 | 30 | 17.2
2 | 2015-10-28 | 21 | 30 | 17.2
2 | 2015-10-29 | 18 | 30 | 17.2
2 | 2015-10-30 | 15 | 30 | 17.2
2 | 2015-10-31 | 12 | 30 | 17.2
2 | 2015-11-01 | 9 | 30 | 17.2
2 | 2015-11-02 | 6 | 30 | 17.2
2 | 2015-11-03 | 3 | 24 | 9.2 | AH: training, log & session handling, KS:User Profiles
2 | 2015-11-04 | 0 | 12 | 0 | PZ: FB login
3 | 2015-11-04 | 40 | 50 | 31.2 | 40: 28h sprint 3 + 12h incomplete tasks from sprint 2
3 | 2015-11-05 | 37.1429 | 44 | 26.2 | LV: friendship task
3 | 2015-11-06 | 34.2857 | 44 | 26.2
3 | 2015-11-07 | 31.4286 | 44 | 26.2
3 | 2015-11-08 | 28.5714 | 32 | 18.2 | AH: subscribe in cybercoach & store data on cybercoach
3 | 2015-11-09 | 25.7143 | 32 | 18.2
3 | 2015-11-10 | 22.8571 | 32 | 18.2
3 | 2015-11-11 | 20 | 32 | 18.2
3 | 2015-11-12 | 17.1429 | 32 | 18.2
3 | 2015-11-13 | 14.2857 | 32 | 18.2
3 | 2015-11-14 | 11.4286 | 32 | 18.2
3 | 2015-11-15 | 8.5714 | 32 | 18.2
3 | 2015-11-16 | 5.7143 | 32 | 18.2
3 | 2015-11-17 | 2.8571 | 32 | 18.2
3 | 2015-11-18 | 0 | 32 | 18.2